## Group Members
SWP 391 |  | SE1812 - .Net |  | Nhóm 5
Members
| 1 | Trần Khánh Linh | HE180134
| 2 | Đào Duy Hiếu | HE180144
| 3 | Nguyễn Quang Minh | HE180148
| 4 | Vũ Đặng Quang Vinh | HE180173
| 5 | Tô Việt Hoàng | HE180179

## Project
STT | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Update | Update detail
| Các chứng năng chính | Tên chức năng | Người dùng | Mô tả chức năng | Người phụ trách | Tình trạng |  | Cập nhật | Chi tiết Cập nhật
1 | Database Design |  | Admin, Manager | Create table in DB: products, brand, cart_details, products_bought, warranty_records, invoice. invoice_Details | Vũ Đặng Quang Vinh | Updating | Iter 1 | None
Tô Việt Hoàng
2 | UI Design | Common | All User | Create Header | Nguyễn Quang Minh | Done | None | None | Link thiết kế giao diện
3 | UI Design | Common | All User | Create Login, Logout | Nguyễn Quang Minh | Done | None | None | https://www.figma.com/design/0oTHiOpmGw0Ij8n3BdrQu7/saler?node-id=201%3A232&t=jabqz1GAE7cICpJX-1
4 | UI Design | Common | All User | Create register page | Nguyễn Quang Minh | Done | None | None
5 | UI Design | Common | All User | Best Seller, Filter Products | Nguyễn Quang Minh | Done | None | None
6 | UI Design | Common | All User | Footer | Đào Duy Hiếu | Done | None | None
7 | UI Design | Common | All User | Product Details | Đào Duy Hiếu | Done | None | None
8 | UI Design |  | Admin | Staff Manager | Đào Duy Hiếu | Done | None | None
9 | UI Design |  | Staff | Product Management | Đào Duy Hiếu | Done | None | None
10 | UI Design |  | Client/Customer | Invoice, Payment | Nguyễn Quang Minh | Done | None | None
11 | Main features |  | User features |  |  | Done | None | None
12 | Main features |  | All users | Login/Logout, View and Change account information | Trần Khánh Linh
13 | Main features |  | Admin | Highest access, Can manage user | Trần Khánh Linh | Done | None | None
14 | Main features |  | Staff | Business management | Vũ Đặng Quang Vinh | Done | Iter 1 | None
15 | Main features |  | Customer | Order, Pay and follow the order(s) | Tô Việt Hoàng | Done | None | None
16 | Main features |  | Viewers | View content | Tô Việt Hoàng | Done | Iter 1
17 | Add demo data for Database |  |  | Create common demo data in Database | Vũ Đặng Quang Vinh | Done | Iter 1 | None
18 | Add demo data for Database |  |  | Meets information and data type requirements | Tô Việt Hoàng | Done | Iter 1 | None
19 | Demo code |  |  | Create web page follow design in order to test user interface | Nguyễn Quang Minh | On going | Iter 1 | None
20 | Demo code |  |  | Edit fit with UI design in order to test user interface | Trần Khánh Linh | On going | Iter 1
21 | Fix the UI and add servlet |  |  | Add missing jsp (ManageNews) | Trần Khánh Linh | Done | Iter 1
22 | Fix the UI and add servlet |  |  | constructs the controllers folder (Account,Admin,Customer,Guest, Manager,Staff,) and views (Account,Admin,Guest,Customer, Manager,Staff) | Trần Khánh Linh | Done | Iter 1
23 | Write html file |  |  | The html file is used to send to the email, they are used to verify account, check orders receipt and warranty_check | Nguyễn Quang Minh | On going | Iter 1
24 | Coding demo |  |  | Write model (Warranty_record,Serial_number,Rate, Product,Product_image, Order,Order_detail,ews,Employee, Discount,Customer,Category, Brand) | Đào Duy Hiếu | Done | Iter 1
25 | Coding demo |  |  | Write dao (Brand,Category,Discount,Employee, News, Order, OrderDetail, Product, Product_image,,Rate,Serial_number, Warranty_record | Tô Việt Hoàng | Updating | Iter 1
26 | Coding demo |  |  | Do filter for types of accounts [Guest,Customer, Employee (Staff, Manager, Admin) ] | Vũ Đặng Quang Vinh | Not Start | Iter 1
27 | Coding demo |  |  | Display and Paging Product from Database | Vũ Đặng Quang Vinh | On going | Iter 1
28 | Coding demo |  |  | Login and Register by verify throught email | Vũ Đặng Quang Vinh | Updating | Iter 1
29 | Coding demo |  |  | Display brands in footer | Tô Việt Hoàng | Done | Iter 1
30 | Code for backend | Manage Account | Admin | Admin/ManageAccount (search by name, select by role,change role) | Trần Khánh Linh | Updating | Iter 2
31 | Code for backend | Manage Feedback | Manager | Feedback;(delete unapproriate feedback) | Trần Khánh Linh | Updating
32 | Code for backend | Manage | Staff | Staff/Manage News(search tittle, change description and short_description) | Trần Khánh Linh | Updating
33 | Code for backend | Manage | Staff | Discount (search by product name, created by user, then filter by role, add and modify discount) | Trần Khánh Linh | Updating
34 | Code for backend | Manage | Admin | Admin/Create staff account | Tô Việt Hoàng | Updating
35 | Code for backend | Manage | Guest | Footer/ListBrand | Tô Việt Hoàng | Done
36 | Code for backend | Manage | Admin | Admin/staff modify history | Tô Việt Hoàng | Updating
37 | Code for backend | Manage | Staff | Staff/Manage Products | Tô Việt Hoàng | Updating
38 | Code for backend | Manage | Guest | ProductList,and orders; | Tô Việt Hoàng | Updating
39 | Code for backend | Manage | Staff | Staff/Warranty | Vũ Đặng Quang Vinh | Done
40 | Code for backend | Views | Guest | Guest Home | Đào Duy Hiếu
41 | Code for backend | Customer | Customer | Shopping History | Đào Duy Hiếu | Updating
42 | Code for backend | Customer | Customer | View profile | Nguyễn Quang Minh | Updating
43 | Code for backend | Customer | Customer | Tracking orders | Nguyễn Quang Minh
44 | Code for backend | Customer | Customer | Cart | Vũ Đặng Quang Vinh | Done
45 | Code for backend | Customer | Customer | Orders | Vũ Đặng Quang Vinh | Done
46 | Code for backend | Account | All users | Filter users (customer or employee) | Vũ Đặng Quang Vinh | Done
47 | Code for backend | Account | All users | Login, register (send otp through email) | Vũ Đặng Quang Vinh | Done
48 | Code for backend | Function for pages | All users | Function for pages | Vũ Đặng Quang Vinh | Done | Iter 2
49 | Code for backend | Manage | Staff | Manage Brands | Tô Việt Hoàng | Done | Iter 2
50 | Paging |  |  | Paging for manage pages, or order pages | Vũ Đặng Quang Vinh | Updating
51 | Upload file |  |  | Upload image file to related table such as products, brands | Tô Việt Hoàng | Done | Iter 2
52 | Change UI template |  |  | Change and merge file from the old version to the new UI template | Trần Khánh Linh | Done | Iter 2
53 | Code for backend | Manage Orders |  | Manage Orders ( search by customer, by product; create orders, delete and update) | Trần Khánh Linh | Done | Iter 2
54 | Code for backend | Manage News |  | Manage News ( update news with the design of the content and the tag of the news) | Trần Khánh Linh | Done | Iter 2
55 | Code for backend | Guest/News Page |  | Load news from data base, with the news details appear by a tag html | Trần Khánh Linh | Done | Iter 2
56 | Code for backend | Guest/Tracking Pages |  | Customer page to traking orders after paid | Trần Khánh Linh | On Going | Iter 2
57 | Code for backend | Guest/Rate Page |  | complete rating pages for customer after receiving orders | Trần Khánh Linh | On Going | Iter 2
58 | Code for backend | Guest/PaymentHistory |  | Create shopping history in case customers want to find the products they had bought | Trần Khánh Linh | Updating | Iter 2
59 | Code for backend | Guest/Header |  | Search by string in header of selling website | Tô Việt Hoàng | On Going | Iter 2
60 | Code for backend | Manage Brands |  | Manage Brand( search brand,create brand, edit brand detail) | Tô Việt Hoàng | Done | Iter 2
61 | Code for backend | Manage Categories |  | Manage Category( search, create , edit) with images for brand | Tô Việt Hoàng | Done | Iter 2
62 | Code for backend | Profile |  | Upload profile of each users | Tô Việt Hoàng | Done | Iter 2
63 | Code for backend | Profile |  | Edit profile | Tô Việt Hoàng | Done | Iter 2
64 | Code for backend | Profile |  | Change email | Tô Việt Hoàng | Updating | Iter 2
65 | Code for backend | Profile |  | Update passwords for customer | Tô Việt Hoàng | Updating | Iter 2
66 | Code for backend | Profile |  | Add avatar for users | Tô Việt Hoàng | On Going | Iter 2
67 | Code for backend | Manage Product |  | Add representative photo for Product | Tô Việt Hoàng | Done | Iter 2
68 | Code for backend | Manage Product |  | Update status for Product (display / hidden) | Tô Việt Hoàng | Done | Iter 2
69 | Code for backend | Manage Brands |  | Update status for Brands (display / hidden) | Tô Việt Hoàng | Done | Iter 2
70 | Code for backend | Manage Categories |  | Update status for Category (display / hidden) | Tô Việt Hoàng | Done | Iter 2
71 | Code for backend | Manage Product |  | Format price when inputting | Tô Việt Hoàng | Done | Iter 2
72 | Code for backend | Statistic |  | Add querry for statistic and complete statistic window | Vũ Đặng Quang Vinh | Updating | Iter 2
73 | Code for backend | Filter Product |  | Filter Product (By Brand, Price, Category) for client | Vũ Đặng Quang Vinh | Done | Iter 2
74 | Code for backend | Filter Product |  | Filter products by relevance ( by name from A-Z, Z-A, by price, low to high, high to low) | Vũ Đặng Quang Vinh |  | Iter 2
75 | Code for backend | Order |  | Order | Vũ Đặng Quang Vinh | Done | Iter 2
76 | Manage warranty | Warranty |  | Manage warranty | Vũ Đặng Quang Vinh | Done | Iter 2
77 | Manage warranty | Warranty |  | Send an email to customer mail, inform the details when staff created warranty for customer | Vũ Đặng Quang Vinh | Updating | Iter 2
78 | Code for backend | Orders |  | Send an email to customer mail, inform the details when customer paid successfully | Vũ Đặng Quang Vinh | Updating | Iter 2
79 | Code for backend | Update order status |  | Send an email to customer mail, inform the details when shippers ship products to customers | Vũ Đặng Quang Vinh | Updating | Iter 2
80 | [5 empty] | Not Start
81 | Analysis products | View statistic |  | Added product analysis (according to warranty and customer feedback/reviews) | Vũ Đặng Quang Vinh | Updating | Iter 3
82 | Analysis products | View statistic |  | Added customer analysis (best-selling products, products with the most and least warranties) | Vũ Đặng Quang Vinh | Updating | Iter 3
83 | Analysis products | View statistic |  | Sell ​​additional products and select the box to view the list by as many days as possible | Vũ Đặng Quang Vinh | Updating | Iter 3
84 |  |  |  | Notifications for products requiring notification | Vũ Đặng Quang Vinh | Updating | Iter 3
85 | Guest/Product details |  |  | Test the buy now button, add plus or minus quantity if the buyer wants to buy the product and redirect immediately to the payment page | Vũ Đặng Quang Vinh |  | Iter 3
86 | Customer/Checkout |  |  | Shipment choose optional payment or COD | Vũ Đặng Quang Vinh | Updating | Iter 3
87 | Staff/Manage Orders, Warranty |  |  | Sent back in April only after receiving the goods and submitting the order | Vũ Đặng Quang Vinh | Updating | Iter 3
88 | Staff/Manage Orders, Warranty |  |  | Add a button so that in button views it is possible to resend invoices and warranty cards to the customer's email | Vũ Đặng Quang Vinh | Not Start | Iter 3
89 | Login | Login by google |  | Login using api google authenticate, if email exist in system count as login, if not count as register customer without username and password (can update later) | Vũ Đặng Quang Vinh | Done | Iter 3
90 | Manage Warranty | Send email warranty |  | Send email to user request book warranty when its accpected or rejected by staff | Vũ Đặng Quang Vinh | Done | Iter 3
91 | SEO |  |  | search optimization for the website |  |  | Iter 3
92 | Employee/Profile.jsp |  |  | Profile for employee | Tô Việt Hoàng | Done | Iter 3
93 | Employee/Profile.jsp |  |  | Update profile (for users login via Google authenticate) in terms username, password, phone and address |  |  | Iter 3
94 | Employee/Profile.jsp |  |  | Validate Edit input in profile Customer Profile page | Tô Việt Hoàng | Done | Iter 3
95 | Staff/Manage Orders, Warranty |  |  | Submit the order after the customer has successfully paid. Add 1 field code order from 8-12 characters | Tô Việt Hoàng |  | Iter 3
96 | Staff/Manage Product |  |  | Align paging to the right, add previous, page 1, next page, last page | Tô Việt Hoàng | Updating | Iter 3
97 | Staff/Manage Product |  |  | Copy the add page to a separate page | Tô Việt Hoàng |  | Iter 3
98 | Staff/Manage Product |  |  | Check all category filters, paging | Tô Việt Hoàng | Done | Iter 3
99 | Staff/Manage Product |  |  | Process price input and read price to the system | Tô Việt Hoàng | Done | Iter 3
100 | Staff/Manage Category |  |  | Check the search bar is not running | Tô Việt Hoàng |  | Iter 3
101 | Home/Search |  |  | Merge code to run search products | Tô Việt Hoàng |  | Iter 3
102 | Customer/ Rate feedback |  |  | Add feedback for each product | Tô Việt Hoàng | Done | Iter 3
103 | Customer/ Rate feedback |  |  | Encrypt sensitive words | Tô Việt Hoàng | Not Start | Iter 3
104 | Staff/Manage Orders |  |  | Customer list management page with customers who buy a lot and have their feedback deleted a lot |  |  | Iter 3
105 | Staff/Manage Orders |  |  | Add columns phone and customer name | Trần Khánh Linh | Done | Iter 3
106 | Staff/Manage Orders |  |  | search by phone, customer name (contain) | Trần Khánh Linh | Done | Iter 3
107 | Staff/Manage Orders |  |  | Filter order status | Trần Khánh Linh | Done | Iter 3
108 | Staff/Manage Orders |  |  | Combo box to update orders status | Trần Khánh Linh | Done | Iter 3
109 | Staff/Manage Orders | Send pdf files to customer |  | Convert HTML to PDF files and save in | Trần Khánh Linh | Done | Iter 3
110 | Staff/Manage Orders | Send pdf files to customer |  | Open pdf files if create success | Trần Khánh Linh | Done | Iter 3
111 | Staff/Manage Orders | Reading content |  | Fix the reading Vietnamese words when convert HTML to PDF | Vũ Đặng Quang Vinh | On Going | Iter 3
112 | Staff/Manage Warranty |  |  | The image section can be flexibly placed below | Trần Khánh Linh | Updating | Iter 3
113 | Staff/Manage Feedback | Delete |  | Delete feedback | Trần Khánh Linh | On Going | Iter 3
114 | Customer/Discount |  |  | Apllied discount to the products, add price before discount | Trần Khánh Linh |  | Iter 3
115 | Staff/Manage Discount | Views, Search |  | Filter discount status, delete unnecessary columns | Trần Khánh Linh | Done | Iter 3
116 | Staff/Manage Discount | Views |  | Handling editing and viewing details | Trần Khánh Linh | Updating | Iter 3
117 | Staff/Manage Discount | Views, Search |  | Optimize search, contains | Trần Khánh Linh | Updating | Iter 3
118 | Staff/Manage News | Views, Add |  | Save Image | Trần Khánh Linh | Done | Iter 3
119 | Staff/Manage News Category | Add |  | Edit category news name | Trần Khánh Linh | Done | Iter 3
120 | Staff/Manage News Category | Update |  | Active or inactive news category | Trần Khánh Linh | Done | Iter 3
121 | Staff/Manage News Category | Delete |  | Delete news category | Trần Khánh Linh | Done | Iter 3
122 | Home/News | Views |  | Groups of news in homes page | Trần Khánh Linh | Updating | Iter 3
123 |  |  |  | Login page for guest/customer and employee, dependently |  |  | Iter 3
124 | Customer/Profile | Update |  | Validate Image Upload for Customer Profile | Tô Việt Hoàng | Done | Iter 3
125 | Customer/Profile | Update |  | Validate Edit input in profile Customer Profile page | Tô Việt Hoàng | Done | Iter 3
126 | Customer/Profile | Update |  | Validate Change Password input in Customer Profile page | Tô Việt Hoàng | Done | Iter 3
127 | Staff/Manage Product | Add |  | Validate Image Upload for Add Product Image | Tô Việt Hoàng | Done | Iter 3
128 | Staff/Manage Product | Edit |  | Validate Image Upload for Edit Product Image | Tô Việt Hoàng | Done | Iter 3
129 | Staff/Manage Brand | Add |  | Validate Image Upload for Add Brand Image | Tô Việt Hoàng | Done | Iter 3
130 | Staff/Manage Brand | Edit |  | Validate Image Upload for Edit Brand Image | Tô Việt Hoàng | Done | Iter 3

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
| Main Features | feature | feature description | manager | status |  |  | Ghi chú
1 | Thiết kế database | Database | Add Category, Voucher, Rate tables | Vũ Đặng Quang Vinh | Done
2 | Main Features | Add a new Actor_SubAdmin | Create additional SubAdmin role. Granted certain rights by Admin | Trần Khánh Linh | Done
3 | Main Features | SubAdmin | Manage vouchers and discounts | Trần Khánh Linh | Updating
4 | Main Features | Viewer | View offers | Trần Khánh Linh
5 | design syste architect | [6 empty] | phan loai ng dung dc tao mo ta chi tiet vai tro cuar cac ator trong he thong de coder hieu |  | 18/5 hoan thien system architect | phan loai ng dung co ban
6 | UI design | Company info | Create additional windows: about us, policy, terms and add the corresponding editing section in the admin dashboard | Hiếu | Updating |  |  |  | https://www.figma.com/design/0oTHiOpmGw0Ij8n3BdrQu7/saler?node-id=0%3A1&t=IIXt5ICScpcDTDhm-1
7 | UI design | News | Add "window edit news" for staff | Hiếu | Updating
8 | UI design | Common | Create a purchase history page | Minh | Updating
9 | UI design | Common | Create a delivery tracking page | Minh | Updating
10 | UI design | Common | Create a warranty claim page | Minh | Updating
11 | UI design | Security | Add forgotten password and reset password sections | Hiếu | Updating
12 | UI design | Security | Add edit account and add product sections for admin and staff | Hiếu | Updating
13 | UI design | Security | Create a NEWS reading page | Minh | Updating
14 | UI design | Security | Create a page to add shipping address before checkout | Minh | Updating
15 | UI design | Security | Create warranty management page | Minh | Updating
16 | Add demo data for database | Database | Edit the database demo again | Vũ Đặng Quang Vinh | Updating
17 | Add demo data for database |  | Fully update information into the system | Tô Việt Hoàng | Updating
18 | Code for UI | UI | Create UI for header, footer, Home, Products List, About us, Policy and Terms, Login/Logout, Confirm Sent Code, Reset and Forgot Password, ManageAccount, News | Trần Khánh Linh | Updating
19 | Code for UI | UI | Create UI pages for Customer ( cart and payment) | Nguyễn Quang Minh | Updating
20 | Code for UI | UI | Create UI pages for Admin, Manager dashboard, including product, news and editing, add Edit | Đào Duy Hiếu | Updating
21 |  | Admin Manage Page | Admin/ManageAccount (search by name, select by role,change role) | Trần Khánh Linh | Updating
22 | Code for backend | Admin Manage Page | Feedback;(delete unapproriate feedback) | Trần Khánh Linh | Updating
23 | Code for backend | Manage | Staff/Manage News(search tittle, change description and short_description) | Trần Khánh Linh | Updating
24 | Code for backend | Manage | Discount (search by product name, created by user, then filter by role, add and modify discount) | Trần Khánh Linh | Updating
25 | Code for backend | Manage | Admin/Create staff account | Tô Việt Hoàng | Updating
26 | Code for backend | Manage | Admin/staff modify history | Tô Việt Hoàng | Updating
27 | Code for backend | Manage | Staff/Manage Products | Tô Việt Hoàng | Updating |  |  | the price range need to format after 000
28 | Code for backend | Manage | ProductList,and orders; | Tô Việt Hoàng | Updating
29 | Code for backend | Manage | Footer/ListBrand | Tô Việt Hoàng | Updating
30 | Code for backend | Manage | Staff/Warranty | Vũ Đặng Quang Vinh | Updating
31 | Code for backend | Customer | Cart,Orders | Vũ Đặng Quang Vinh | Updating
32 | Code for backend | Guest | Home | Đào Duy Hiếu
33 | Code for backend | Customer | Shopping History | Đào Duy Hiếu | Updating
34 | Code for backend | Customer | View profile | Nguyễn Quang Minh | Updating
35 | Code for backend | Customer | Tracking orders | Nguyễn Quang Minh
36 | Code for backend | Account | Filter users (customer or employee) | Vũ Đặng Quang Vinh | Updating
37 | Code for backend | Account | Login, register (send otp through email) | Vũ Đặng Quang Vinh | Updating
38 | Code for backend | Function for pages | Function for pages | Vũ Đặng Quang Vinh | Updating

## Iter 2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature Name1 | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Paging |  | Paging for manage pages, or order pages | Vũ Đặng Quang Vinh | Updating
2 | Upload file |  | Upload image file to related table such as products, brands | Tô Việt Hoàng | Done
3 | Change UI template |  | Change and merge file from the old version to the new UI template | Trần Khánh Linh | Done
4 | Code for backend | Manage Orders | Manage Orders ( search by customer, by product; create orders, delete and update) | Trần Khánh Linh | Done
5 | Code for backend | Manage News | Manage News ( update news with the design of the content and the tag of the news) | Trần Khánh Linh | Done
6 | Code for backend | Guest/News Page | Load news from data base, with the news details appear by a tag html | Trần Khánh Linh | Done
7 | Code for backend | Guest/Tracking Pages | Customer page to traking orders after paid | Trần Khánh Linh | On Going
8 | Code for backend | Guest/Rate Page | complete rating pages for customer after receiving orders | Trần Khánh Linh | On Going
9 | Code for backend | Guest/PaymentHistory | Create shopping history in case customers want to find the products they had bought | Trần Khánh Linh | Updating
10 | Code for backend | Guest/Header | Search by string in header of selling website | Tô Việt Hoàng | On Going
11 | Code for backend | Manage Brands | Manage Brand( search brand,create brand, edit brand detail) | Tô Việt Hoàng | Done
12 | Code for backend | Manage Categories | Manage Category( search, create , edit) with images for brand | Tô Việt Hoàng | Done
13 | Code for backend | Profile | Upload profile of each users | Tô Việt Hoàng | Done
14 | Code for backend | Profile | Edit profile | Tô Việt Hoàng | Done
15 | Code for backend | Profile | Change email | Tô Việt Hoàng | Updating
16 | Code for backend | Profile | Update passwords for customer | Tô Việt Hoàng | Updating
17 | Code for backend | Profile | Add avatar for users | Tô Việt Hoàng | On Going
18 | Code for backend | Manage Product | Add representative photo for Product | Tô Việt Hoàng | Done
19 | Code for backend | Manage Product | Update status for Product (display / hidden) | Tô Việt Hoàng | Done
20 | Code for backend | Manage Brands | Update status for Brands (display / hidden) | Tô Việt Hoàng | Done
21 | Code for backend | Manage Categories | Update status for Category (display / hidden) | Tô Việt Hoàng | Done
22 | Code for backend | Manage Product | Format price when inputting | Tô Việt Hoàng | Done
23 | Code for backend | Statistic | Add querry for statistic and complete statistic window | Vũ Đặng Quang Vinh | Updating
24 | Code for backend | Filter Product | Filter Product (By Brand, Price, Category) for client | Vũ Đặng Quang Vinh | Done
25 | Code for backend | Filter Product | Filter products by relevance ( by name from A-Z, Z-A, by price, low to high, high to low) | Vũ Đặng Quang Vinh
26 | Code for backend | Order | Order | Vũ Đặng Quang Vinh | Done
27 | Manage warranty | Warranty | Manage warranty | Vũ Đặng Quang Vinh | Done
28 | Manage warranty | Warranty | Send an email to customer mail, inform the details when staff created warranty for customer | Vũ Đặng Quang Vinh | Updating
29 | Code for backend | Orders | Send an email to customer mail, inform the details when customer paid successfully | Vũ Đặng Quang Vinh | Updating
30 | Code for backend | Update order status | Send an email to customer mail, inform the details when shippers ship products to customers | Vũ Đặng Quang Vinh | Updating

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature Name1 | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Analysis products | View statistic | Added product analysis (according to warranty and customer feedback/reviews) | Vũ Đặng Quang Vinh | Updating
2 | Analysis products | View statistic | Added customer analysis (best-selling products, products with the most and least warranties) | Vũ Đặng Quang Vinh | Updating
3 | Analysis products | View statistic | Sell ​​additional products and select the box to view the list by as many days as possible | Vũ Đặng Quang Vinh | Updating
4 |  |  | Notifications for products requiring notification | Vũ Đặng Quang Vinh | Updating
5 | Guest/Product details |  | Test the buy now button, add plus or minus quantity if the buyer wants to buy the product and redirect immediately to the payment page | Vũ Đặng Quang Vinh
6 | Customer/Checkout |  | Shipment choose optional payment or COD | Vũ Đặng Quang Vinh | Updating
7 | Staff/Manage Orders, Warranty |  | Sent back in April only after receiving the goods and submitting the order | Vũ Đặng Quang Vinh | Updating
8 | Staff/Manage Orders, Warranty |  | Add a button so that in button views it is possible to resend invoices and warranty cards to the customer's email | Vũ Đặng Quang Vinh | Not Start
9 | Login | Login by google | Login using api google authenticate, if email exist in system count as login, if not count as register customer without username and password (can update later) | Vũ Đặng Quang Vinh | Done
10 | Manage Warranty | Send email warranty | Send email to user request book warranty when its accpected or rejected by staff | Vũ Đặng Quang Vinh | Done
| SEO |  | search optimization for the website | Vũ Đặng Quang Vinh | Done
11 | Employee/Profile.jsp |  | Profile for employee | Tô Việt Hoàng | Done
12 | Employee/Profile.jsp |  | Update profile (for users login via Google authenticate) in terms username, password, phone and address | Vũ Đặng Quang Vinh | Done
13 | Employee/Profile.jsp |  | Validate Edit input in profile Customer Profile page | Tô Việt Hoàng | Done
14 | Staff/Manage Orders, Warranty |  | Submit the order after the customer has successfully paid. Add 1 field code order from 8-12 characters | Tô Việt Hoàng
15 | Staff/Manage Product |  | Align paging to the right, add previous, page 1, next page, last page | Tô Việt Hoàng | Updating
16 | Staff/Manage Product |  | Copy the add page to a separate page | Tô Việt Hoàng
17 | Staff/Manage Product |  | Check all category filters, paging | Tô Việt Hoàng | Done
18 | Staff/Manage Product |  | Process price input and read price to the system | Tô Việt Hoàng | Done
19 | Staff/Manage Category |  | Check the search bar is not running | Vũ Đặng Quang Vinh | Done
20 | Home/Search |  | Merge code to run search products | Vũ Đặng Quang Vinh | Done
21 | Customer/ Rate feedback |  | Add feedback for each product | Tô Việt Hoàng | Done
22 | Customer/ Rate feedback |  | Encrypt sensitive words | Tô Việt Hoàng | Not Start
23 | Staff/Manage Orders |  | Customer list management page with customers who buy a lot and have their feedback deleted a lot
24 | Staff/Manage Orders |  | Add columns phone and customer name | Trần Khánh Linh | Done
25 | Staff/Manage Orders |  | search by phone, customer name (contain) | Trần Khánh Linh | Done
26 | Staff/Manage Orders |  | Filter order status | Trần Khánh Linh | Done
27 | Staff/Manage Orders |  | Combo box to update orders status | Trần Khánh Linh | Done | 1-Pending,2-Reject,3-Packaging,4,Shipping, 5-Received,6-Return,7-Receive goods back
28 | Staff/Manage Orders | Send pdf files to customer | Convert HTML to PDF files and save in | Trần Khánh Linh | Done
29 | Staff/Manage Orders | Send pdf files to customer | Open pdf files if create success | Trần Khánh Linh | Done
30 | Staff/Manage Orders | Reading content | Fix the reading Vietnamese words when convert HTML to PDF | Vũ Đặng Quang Vinh | On Going
31 | Staff/Manage Warranty |  | The image section can be flexibly placed below | Trần Khánh Linh | Updating
32 | Staff/Manage Feedback | Delete | Delete feedback | Trần Khánh Linh | On Going
| Customer/Discount |  | Apllied discount to the products, add price before discount | Trần Khánh Linh
34 | Staff/Manage Discount | Views, Search | Filter discount status, delete unnecessary columns | Trần Khánh Linh | Done
35 | Staff/Manage Discount | Views | Handling editing and viewing details | Trần Khánh Linh | Updating
36 | Staff/Manage Discount | Views, Search | Optimize search, contains | Trần Khánh Linh | Updating
37 | Staff/Manage News | Views, Add | Save Image | Trần Khánh Linh | Done
38 | Staff/Manage News Category | Add | Edit category news name | Trần Khánh Linh | Done
39 | Staff/Manage News Category | Update | Active or inactive news category | Trần Khánh Linh | Done
40 | Staff/Manage News Category | Delete | Delete news category | Trần Khánh Linh | Done
41 | Home/News | Views | Groups of news in homes page | Trần Khánh Linh | Updating
42 |  |  | Login page for guest/customer and employee, dependently
43 | Customer/Profile | Update | Validate Image Upload for Customer Profile | Tô Việt Hoàng | Done
44 | Customer/Profile | Update | Validate Edit input in profile Customer Profile page | Tô Việt Hoàng | Done
45 | Customer/Profile | Update | Validate Change Password input in Customer Profile page | Tô Việt Hoàng | Done
46 | Staff/Manage Product | Add | Validate Image Upload for Add Product Image | Tô Việt Hoàng | Done
47 | Staff/Manage Product | Edit | Validate Image Upload for Edit Product Image | Tô Việt Hoàng | Done
48 | Staff/Manage Brand | Add | Validate Image Upload for Add Brand Image | Tô Việt Hoàng | Done
49 | Staff/Manage Brand | Edit | Validate Image Upload for Edit Brand Image | Tô Việt Hoàng | Done
50 | Account/Register | Add | Validate Input for Register page | Tô Việt Hoàng | Done